## Sheet1
|  | 2015 | 2016 | [13 empty] | 2017 | [6 empty] | 2018
|  | December (M2) | January (M3) | February (M4) | March (M5) | April (M6) | May (M7) |  | June (M8) | July (M9) | August (M10) | September (M11) | October (M12) | November (M13) |  | December (M14) | Jan-Feb-Mar (M15-16-17) |  | Apr-May-June (M18-19-20) |  | July-Aug-Sept (M21-22-23) | Oct-Nov-Dec (M24-25-26) |  | Jan-Feb-Mar (M27-28-29) | Apr-May-June (M30-31-32) |  | July-Aug-Sept (M33-34-35) | October (M36) |  | Nov | December
WP1 |  |  | Upload to participant portal (ethics) "data protection agency copies" | Del 1.1 Internal communication strategy |  | Del.1.2+1.4 Risk Management Plan + Data Management Plan | INTERNAL REPORT (period 01/11/2015-30/04/2016) – DEADLINE 20/05/2016 | [6 empty] | INTERNAL REPORT (period 01/05/2016-31/12/2016) – DEADLINE 20/11/2016 | SC Skype Meeting |  | INTERMEDIATE OFFICIAL REPORT (01/11/2015-31/01/2017) – DEADLINE 20/02/2017 | Send interim report to EC (31/03/2017) | BRISTOL INTERMEDIATE MEETING (April 2017, except Easter holidays 8th-17th) |  |  | INTERNAL REPORT (period 01/02/2017-31/10/2018) – DEADLINE 20/11/2017 | Del 1.3 Advisory Board Report + SC Skype Meeting (Nov) |  | INTERNAL REPORT (period 01/11/2017-30/04/2018) – DEADLINE 20/05/2018 | SC Skype Meeting (May) |  | FINAL MEETING AND CONFERENCE IN PARIS |  | FINAL OFFICIAL REPORT (01/02/2017-31/10/2018) – DEADLINE 20/11/208 | Send final report to EC (20/12/2018)
WP2 | Paris | 2.1. Choose and contact 4 schools (LAC) + Co-create with other CSC dynamics for W1 | Create dynamics about 1 or 2 RRI keys for W2 + Adapt otherCSC dynamics for W2 | Execute W1 in 4 schools (8 groups) (LAC) | Execute W2 in 4 schools (8 groups) + Report on Paris workshops (LAC) | Creation and rehearsal of CSC PERSEIA (March-Apr-May)(LAC) |  | Performing PERSEIA in our 4 schools/museums (LAC) Performing PERSEIA in our 4 schools/museums (LAC) |  |  |  | Performing CSC PERSEIA in 10 UNESCO list schools + Design of participatory workshops 2.2. | Design and adapt 5 workshops |  |  |  |  | Deliver 5 workshops + Start to create and rehearse students' PERSEIA (LAC) (Feb-May) + Include early career researchers (Jan) |  | Students' performance of their PERSEIA (LAC) |  |  |  | Deliver participatory workshops/rehearsal/delivery PERSEIA (until end September) + Knowledge-transfer to museum facilitators 2.3. + 2.2.(Bristol) Deliver workshops and students develop PERSEIA (Perform at BIG BANG?) |  | D2.2.Protocol to generate participative processes
| Barcelona | 2.1. Choose and contact 4 schools |  | Work with focus (working?) groups 2.1 |  | Creation and rehearsal of CSC PERSEIA (Apr-May) |  |  | Deliver of PERSEIA (10-16 schools) 2.1. |  |  | Design of participatory workshops 2.2. |  |  | SC Skype Meeting + Deliver PERSEIAS + Design of participatory workshops 2.2. | Design of participatory workshops 2.2. |  | Participatory process to create PERSEIAs 2.2 + D2.1 Protocol to generate PERSEIA |  | Participatory process to create PERSEIAs 2.2 +Delivering of PERSEIAs by highschool students 2.2. |  |  | SC Skype Meeting (Nov) |  |  | Scale up PERSEIAs to museums 2.3. + D2.2.Protocol to generate participative processes + SC Skype Meeting (May) |  |  | D2.3. Guidelines for PERSEIA adaptation to science-museums
| Bristol | 2.1. Choose and contact 4 schools + work on content for focus groups | Work on creation and adaptation of focus groups activity | Deliver 4 focus groups in schools | Creation of SMS PERSEIA + Contribute to knowledge sharing workshop (March-April-May) |  |  | Creation of SMS PERSEIA + Contribute to knowledge sharing workshop | Talk to schools + Deliver of SMS PERSEIA (6+6 schools) 2.1. |  |  |  | Attend RRI reflexivity training in France |  |  | Selection of topics (at schools) A |  | Selection of topics B + Deliver participatory workshops in 2 schools + 2.2. Students Perform at BIG BANG? / Critical thinking, Interaction Arts & Science, Gender Issues |  | Performing skills B | [5 empty] | Contribute to museums event 2.3. + D2.2.Protocol to generate participative processes | Contribute to find conference!
WP3 | Paris |  |  |  |  | Knowledge sharing workshop | [6 empty] | Reflexivity workshop in France with ERCs and relevant partners |  | Training 1 week | [5 empty] | WP 3.2. Analyse data and present results and recommendations from summative evaluation of Researcher training (UoB+UoW) + evaluation of trainings and toolkits (Barcelona) |  | 2nd training Paris Bristol Barcelona + 1st version toolkit + 2nd training teachers(also 2018 and according to schools and countries) + SC Skype Meeting (Nov) | 2nd training teachers(also 2018 and according to schools and countries) |  |  |  |  | Final version toolkits
| Barcelona | [13 empty] | Training (2 sets of sessions)
| Bristol | Gathering info from partners, researchers and teachers for knowledge sharing workshop |  | Develop plan for evaluation for trainings |  |  |  | Developing plan for training summative evaluation (Researcher Training) 3.2 (UoB+UoW) Developing plan for training summative evaluation (Researcher Training) 3.2 (UoB+UoW) Meeting |  | Setting up system for summative evaluation of researcher training (round 1) 3.2 (UoB+UoW) |  |  |  |  | SC Skype Meeting |  |  | Training (different weeks) | [7 empty] | SC Skype Meeting (May)
WP4 | Paris | Deliver list with requirements to schools (UAB) + Design activity on participation for WP2 (proposal) (UAB) + Literature review expert-based indicators assessment criteria (dec-apr) (UAB) | Define scope for automated analysis tool (platforms)(UoW)+ Design activity on participation (guidelines for WP2 CSC) (UAB) | Set-up social media scraping tool on practice partners social media accounts to start gathering test data (UoW) WP4.2 | Preliminary qualitative analysis of social media content from practice partners social media feeds to identify proposed automated analysis categories (UoW) WP4.2 + Support in the participation activity within WP2 workshops (UAB) | Audience Impact Evaluation of performances (set up and conduct) BONUS TASK (UAB) |  | Del 4.1. Literature review assessment indicators | WP 4.2. Set-up and test automated social media analysis tool (ends with on-going analysis commencing)(UoW) | [10 empty] | WP4.2. Conduct small scale online ethnography on sample of PERFORM events (yielding research report)(UoW) | [6 empty] | WP4.2. Analysis and writing of automated social media analysis results (UoW) |  | Del 4.3 Policy brief (contributions of PERSEIA)
| Barcelona | [8 empty] | Assessment design (strategy, collection tools)(share with WP2) from June to October (UAB) |  |  |  |  | SC Skype Meeting | Start Data collection and analysis (UAB) | [6 empty] | SC Skype Meeting (Nov) |  |  | Writing Policy guidelines (analysis conclusions) (UAB) + SC Skype Meeting (May)
Bristol
WP5 | [14 empty] | Nov. 10th: UNESCO World Science Day + SC Skype Meeting |  |  | Sustainability Plan |  | 1st Policy Brief | Start policy impact |  | SC Skype Meeting (Nov) + SC Skype Meeting (Nov) |  |  | SC Skype Meeting (May) | 2nd Policy Brief
WP6 |  | Start designing communication strategy and plan | Start building relations with other communities | Start developing of communication plan | Website launch and social media | [6 empty] | Launch a call among EUSEA members to host performances |  |  | SC Skype Meeting | [5 empty] | Launch and invitation to the final conference |  | Launch and invitation to the final conference + SC Skype Meeting (Nov) |  |  | SC Skype Meeting (May) | Final conference