**WP6 break-out groups session**

**Part of the morning and afternoon of day 1 (April 10th), and part of the morning and afternoon of day two (April 11th): Final Conference Working Group**

**Participants: Casimiro, Louis, Wendy, Rachel and Marina.**

AT presented the suggested programme and the list of things that we had to achieve in this working group. Here is the list, the results and below, some notes about the discussions.

|  |  |
| --- | --- |
| Dates for the Conference | 14 or 15 or 21 or 22 of JUNE 2018 |
| Define in detail and agree on the programme | We changed the proposal that we discussed with Leo. Then we changed again the programme. The 2 versions are at the end of Day 1.  Agreement: We have to have the FINAL programme in MARCH 2018 and Disseminate the CONFERENCE on April 1st onwards. |
| Keynote Speakers | April 2017: Leo starts contacting Roberto Begnini and Casimiro must inform about formalities requested by the UNESCO  Roberto Begnini  Maria Acaso  Sir Ken Robinson  Alan Balda  Kalinga Prizes |
| Responsibilities and work plan | Before May 15th Casimiro and Leo must draft a letter and send it to Helena and Uriol (WP2 general leader) cc Coordinator, explaining to each WP2 Leader in UK, France and Spain, what to talk and ask to the teachers related to the Conference: which of the dates would be the best for them. |
| Budget | By April 30. 2017 Casimiro must send Leo and the Coordinator the detailed budget with all the items that must be covered and a view about budget available for covering students & teachers’ costs.  Leo must do the same with the budget of EUSEA related to the Conference. |
| Conference content | Casimiro and Leo:  Have a track of the version of WP3 that has to be prepared for the Conference, do this with the Coordinator. |

The idea of calling it a ConFest was liked by everyone but at the end of the meeting we realised that there was no real festival-like activity in the programme, so we should not call it like that.

Regarding the idea of opening a call for Eusea members to participate, it was not considered practical, because there are so many things to show in a short period of time, so something that comes from outside was not a good idea.

The first suggestion was to divide the day in two parts, concentrating the show only during the morning, as most of the Policy makers, delegates and other stakeholders won´t stay the whole day. During the afternoon the activities will be project related, Perseias and Toolkit. The toolkit won´t be ready by June but the University of Bristol will present a version of what has been achieved at that point.

Discussions about the date:

We don´t want to choose a date when we risk not having any student at all.

We want to show the students performing so we want to have the Perseias there: first we thought students performing live and then we realised it would be terrifying for them, so it was suggested to present a video showing what happened in every country.

We will ask the teachers about which date suits them best: Casimiro and Leo will write the invitation, explaining the whole picture and their role. They will contact each WP2 leader in each country, cc the Coordination Team.

Do we have budget for the Perseias schools? Casimiro will firstly look at UNESCO Budget and EUSEA must do the same. After this, every partner will explore their budgets to see if they can support this item.

What do we expect from the Speakers?

1. That they are available
2. Relevant link with science comms
3. Link with Performing arts
4. Inspiring with content
5. Scientific background (not exclusively) but a commitment
6. Diversity, gender and developing countries (India, South Africa?)

Videos in the middle of conference and Casimiro suggests to make videos about Marketing campaign

Perseias presentation

Things that might not work: other commitments, money, time, and permissions.

Rachel (SMS) thinks that it might happen that NO students come, at least from the UK.

We have to find out this VERY soon, if they do have interest, intention and of course BUDGET.

Organise the numbers of Students and teachers with the partners that worked with the schools.

Toolkit Snapshot: New deadline to be agreed with UoB (Researchers, teachers, July and October final version) Tbvt ( Museums) Students.

The students, meeting with the students with other students from France or Spain is a great thing, we should do our best to make this happen.

Livio came with the idea of a Radio Show to present the project and its different components. The stage is set as a radio studio, and there is a puppet that is the presenter. He interviews the different people that participated in the project and he invites the public to ask as being the listeners of the radio show. [See example here](https://hubic.com/home/pub/?ruid=aHR0cHM6Ly9sYjk5MTEuaHViaWMub3ZoLm5ldC92MS9BVVRIX2M0ZDk2OWY1MjBkNTU2NjNhZDA3MzIyN2IwMTA0ZDljL2RlZmF1bHQvLm92aFB1Yi8xNDkxOTgzOTQ2XzE0OTQ1NzU5NDY/dGVtcF91cmxfc2lnPWE2OGVkOWUxOTk5NjFjYzIxMWZkYzUwN2IxNzgzMDNhYTMyZjZkZDgmdGVtcF91cmxfZXhwaXJlcz0xNDk0NTc1OTQ2)

c) First version of the Final Conference Programme ( made by the Bristol Working Group)

Moderator: Casimiro Vizzini

|  |  |
| --- | --- |
| 9:00-10:00 | Registration and Coffee |
| 10:00-10:20 | Welcome words: UNESCO and Isabel |
| 10:20-11:00 | Show of 2 partners + Videos about Students |
| 11:00-11:30 | Keynote Speaker 1 |
| 11:30-12:00 | Coffee Break |
| 12:00-12:20 | Show |
| 12:20-13:00 | Keynote Speaker 2 |
| 13:00-14:30 | L U N C H |
| 14:30-15:30 | Perseias Presentation |
| 15:30-15:50 | Open questions |
| 15:50-16:20 | Coffee Break |
| 16:20-17:00 | Toolkit presentation: Researchers and Teachers |
| 17:00-17:30 | Wrapping up and Farewell words |

Second version of the Final Conference Programme ( made by the Bristol Working Group)

Moderator: Casimiro Vizzini

|  |  |
| --- | --- |
| 9:00-10:00 | Registration and Coffee |
| 10:00-10:20 | Welcome words: UNESCO and Isabel |
| 10:20-10:50 | Keynote Speaker 1 |
| 10:50-11:20 | Radio Show: Videos of Perseias and Partners |
| 11:20-11:50 | Coffee Break |
| 11:50-12:30 | Radio Show: Interviews |
| 12:30-13:00 | Keynote Speaker 2 |
| 13:00-14:30 | L U N C H |
| 14:30-15:30 | Perseias Presentation |
| 15:30-15:50 | Open questions |
| 15:50-16:20 | Coffee Break |
| 16:20-17:00 | Toolkit presentation: Researchers and Teachers |
| 17:00-17:30 | Wrapping up and Farewell words |