## Hoja1
|  | 2017 | [8 empty] | 2018
WP | Case study | April | May | June | July | August | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December
WP1 |  | 2017 April: External evaluation meeting; 2017 May: AB contact for reporting; 2017 September: Steering Committee; 2017 October: D1.3; 2017 December: 3rd internal newsletter; 2018 April: Milestone 3; 2018 June: 4th internal newsletter; 2018 October: Final consortium meeting; 2018 November: Final report
|  | Milestone 3 | [5 empty] | 3rd internal report | [5 empty] | 4th internal report
WP2 | Spain | 2017 April: Contact schools (Broggi + Consell); 2017 June: User friendly guidelines from D2.1
|  |  |  | PW redesign |  |  | 15th, first draft of PW | 15-30th, final protocol of PW |  | Milestone 4 | PW implementation |  |  | D2.2 |  | PERSEIA implementation in science museum |  |  |  | D2.3
| France | 2017 April: Last PW of first round; 2017 June: Play in 3 schools (task 2.1); 2017 July: Design of PW; 2018 January: Second round of PW
PERSEIA Marie Curie
School recruiting
| UK | 2017 July: School gala; 2018 January: PW1 and PW2; 2018 February: PW3 and PW4; 2018 March: Students' PERSEIAs performance; 2018 April: UoB scools visit + WP4 evaluation
PW development
[5 empty] | Meeting with UoB for PW development | Participatory process re-design & participatory process protocol draft (15 Aug-15 Sept)
CSC share first draft of participatory process with consortium (mid-Sept)
WP3 | Spain | 2017 May: ECR evaluation work with WP4 in Barcelona (15-17th); 2017 July: Teachers' training; 2017 November: ECR training; 2018 July: Teachers' training
| France | 2017 September: Teachers' training start; 2017 October: ECR recruiting; 2017 November: ECR training (28-29); 2018 February: Teachers' training; 2018 April: Teachers' training end
| UK | 2017 May: Toolkit development
[17 empty] | D3.1 |  |  | D3.2
WP4 | Spain | 2017 April: Implementation Assessment Strategy; 2017 June: Analysis of results (April - July); 2017 July: Sharing of results; 2017 October: Review assessment strategy
|  | Data collection task 4.2. | [5 empty] | Milestone 4
| France | 2017 April: Implementation Assessment Strategy (April- June); 2017 June: Analysis of results; 2017 July: Sharing of results; 2017 October: Review assessment strategy
Data collection task 4.2.
| UK | 2017 April: Implementation Assessment Strategy; 2017 June: Analysis of results; 2017 July: Sharing of results; 2017 October: Review assessment strategy
Data collection task 4.2. alternative to social media
Focus groups + interviews+ visit UoB
WP5 |  | 2017 August: Roundtable meetings with electoral groups of UNESCO MS; 2017 November: World Science Forum 7th-11th; 2018 July: ESOF 2018 9th-14th; 2018 August: Policy Briefing 2; 2018 October: Reporting
WP6 |  | 2017 April: Send Fb + Twitter guidelines; 2017 May: Videos for dissemination; 2018 March: Final version of the programme for final conference; 2018 April: Dissemination of the final conference; 2018 June: FINAL CONFERENCE; 2018 October: Reporting
|  | Organisation of final conference | Contact more networks for dissemination purposes | [10 empty] | PSCT 2018
Production and edition of videos
Post facebook, twitter, instagram about the project
Tackling of dissemination done by partners
EC open doors days