**PERFORM fourth internal report: M25 (November 2017) –M30 (April 2018)**

|  |  |  |  |
| --- | --- | --- | --- |
| April, 2018 | Technical report #4:**submission of M16-M24 activities by WP leaders to partners** | April, 20th | WP leaders |
| Communication of **dissemination activities partners to CT** | April, 27th | All |
| May, 2018 | Timesheets and financial report:**Submission of M16-M24 update by partners to CT** | May, 4th | All |
| Technical report #4:**submission of feedback by partners to WP leaders** | May, 4th | All |
| Technical report #4:**final version circulated by WP to CT** | May, 20th | WP leaders |
| Technical report #4:**final version circulated by CT topartners** | May, 29th | CT |